## Sheet1
Stage | Activity | set1 | set2 | set3
Initiation | Sponsor Contacts CT Co-ord/Mgr or PI | 1 | 1 | 1
| Refer to SSS or Co-ordinator | 1 | 1 | 1
| Complete CDA | 1 | 3 | 21
| Sponsor Provides Protocol | 1 | 1 | 1
| Co-ord and PI explore further - read Protocol | 5 | 7 | 15
| Receive Key Trial Information from Sponsor | 5 | 22 | 84
| Provide Trial Start Up information to Sponsor | 1 | 1 | 1
| Feasibility Assessment by PI and Co-ord | 4 | 6 | 6
| Site Assessment Visit or Phonecall | 1 | 1 | 1
| Decision by Sponsor/CHS that Trial is Feasible | 1 | 1 | 1
Stage 1 Submission | Acquire Relevant Docs from CHS (CDA and SPA Report) | 4 | 2 | 1
| Complete CTMG Submission Forms (Feas & Gov Sheet) | 18 | 2 | 12
| Develop Required Docs (Plain Language Summary) | 1 | 1 | 18
| Obtain PI Approval | 1 | 1 | 6
| Send REGO Submission for CTMG Meeting | 1 | 1 | 1
| CTMG Meeting | 1 | 1 | 1
| Notice received of Approval to Proceed | 1 | 1 | 1
Stage 2:Step A | Request Provider Quotes | 1 | 4 | 31
| Receive Provider Quotes | 46 | 9 | 38
Step B | Request Relevant Docs from Sponsor | 1 | 97 | 36
| Supply CTRA and Budget to Finance Team | 1 | 1 | 1
| Update CTRA Schedule 1 and 2 | 99 | 97 | 38
| Draft Budget Spreadsheet | 8 | 53 | 30
| Finance and Co-ord Review Budget | 1 | 1 | 1
| Negotiate Budget with Sponsor | 108 | 81 | 38
| Prepare Finance Summary | 1 | 1 | 1
Step C | Lead Site Approval Date | 1 | 1 | 1
| Lead Site Approval Letter and Documents Received | 8 | 1 | 77
| PICF's Updated | 50 | 14 | 35
| Sponsor Approval of PICF's | 1 | 1 | 1
Step D | Preparation of Submission Documents | 121 | 140 | 176
| Submit for REGO with all attachments | 1 | 1 | 1
| REGO provide Approval | 1 | 1 | 1
Set Up | Create Visit Payment Schedule | 2 | 3 | 3
| Create Patient List | 1 | 3 | 2
| Creat Source Documents for Visits | 5 | 15 | 20
| Site Initiation Visit | 1 | 1 | 1
| Invoice Sponsor for Start Up Fee | 1 | 1 | 1
| Receive Notification of Site Activation | 1 | 1 | 1