## Sheet1
Activity | Min | Max
Request Provider Quotes | 1 | 14
Receive Provider Quotes | 14 | 180
Request Relevant Docs from Sponsor | 1 | 14
Supply CTRA and Budget to Finance Team | 1 | 5
Update CTRA Schedule 1 and 2 | 1 | 14
Draft Budget Spreadsheet | 1 | 28
Finance and Co-ord Review Budget | 1 | 2
Negotiate Budget with Sponsor | 1 | 28
Prepare Finance Summary | 1 | 2
Lead Site Approved | 1 | 270
Lead Site Approval Letter and Documents Received | 5 | 90
PICF's Updated | 1 | 60
Sponsor Approval of PICF's | 3 | 60
Preparation of Submission Documents | 60 | 360
Submit for REGO with all attachments | 1 | 5
REGO provide Approval | 14 | 56